## Sheet1
Student | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
Ashwin | As a user, I need two shapes - denoting a pair of angular brackets, so that they denote the start & end of an if condition | Knowledge gathering on java graphics and custom shapes | 3 | 0 | 0 | 0 | 0 | 0 | 3
|  | Create a class structure for the angular open brackets and corresponding attributes | 0 | 1 | 1 | 1 | 0 | 0 | 3
|  | Create a class structure for the angular close brackets and corresponding attributes | 0 | 0 | 2 | 0 | 0 | 0 | 2
|  | Changes to add a dot inside the open bracket shape to signify the input connection for the shape | 0 | 0 | 1 | 1 | 1 | 0 | 3
|  | Changes to add a dot inside the close bracket shape to signify the output connection for the shape | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Test the changes upon selection of the each shape and it's connectivity when dropped on each workspace | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Total Hours | [6 empty] | 13
Ashutosh | As a user, I need a shape denoting “-” symbol, so that it acts as a value holder block | Knowledge Acquisition on JDialog. | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Implementation of a JDialog with the frame, text box & button as per the requirements. | 0 | 3 | 0 | 0 | 0 | 0 | 3
|  | Add the close and minimize funtionality to the dialog. | 0 | 0 | 1 | 1 | 0 | 0 | 2
|  | Save the text value in the text box to the object of the current shape. | 0 | 0 | 1 | 1 | 0 | 0 | 2
|  | Verify the text value in the the object of the current shape loads in the text box. | 0 | 0 | 0 | 1 | 1 | 0 | 2
|  | Unit test the funtionality of the "-" shape. | 0 | 0 | 0 | 0 | 3 | 0 | 3
|  | Total Hours | [6 empty] | 14
Chandan | As a user, I should be able to create a new tab on the click of a button so that I can use it as a new workspace. | Knowledge Acquisition on JTabs and creating multiple tabs. | 2 | 0 | 0 | 0 | 0 | 0 | 2
|  | Implementation of multiple tabs on click of a button | 2 | 1 | 0 | 0 | 0 | 0 | 3
|  | Create a function call to check the current tab that is selected. | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Change the class structure to compily with the previous code structure and extend last code | 0 | 1 | 1 | 1 | 0 | 0 | 3
|  | Add the tabs to the frame and wrap them. | 0 | 0 | 1 | 2 | 0 | 0 | 3
|  | Test the changes on click of the New space button | 0 | 0 | 0 | 1 | 1 | 0 | 2
|  | Total Hours | [6 empty] | 15
Nachi | As a user, I need a frame with seven shapes on the left-hand side of the screen. | Include all the new shapes as per the reqirement. | 3 | 1 | 0 | 0 | 0 | 0 | 4
|  | Create an icon for each of the shapes | 1 | 2 | 0 | 0 | 0 | 0 | 3
|  | Add the icons created to the buttons placed on the left panel. | 0 | 2 | 1 | 1 | 0 | 0 | 4
|  | The selected shape button highlighted on click | 0 | 0 | 1 | 2 | 1 | 0 | 4
|  | Add the currently selected shape details to a variable for identification in the workspace. | 0 | 0 | 0 | 1 | 1 | 0 | 2
|  | Unit test the changes to if all buttons are displayed and are clickable. | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Total Hours | [6 empty] | 18
Srini | As a user, I need two shapes - denoting a pair of round brackets, so that they denote the start & end of a function block. | Knowledge Acquistion on java Graphics | 2 | 0 | 0 | 0 | 0 | 0 | 2
|  | Create a class structure for the open brackets and add 1 output dot in right side of the shape | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Create a class structure for the close brackets and add 1 input dot in left side of the shape | 0 | 1 | 1 | 0 | 0 | 0 | 2
|  | Add mouse click listener to draw 1 line from the output dot of open round bracket | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  | Add mouse click listener to draw 1 line to the input dot of close round bracket | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Test the changes upon selection of the each shape and it's connectivity when dropped on each workspace | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Total Hours | [6 empty] | 9
Srini | As a user, I need a shape denoting two parallel bars, so that it acts as a one - to - many or many - to - one connecting structure. | Create a class structure for the '¦¦' shape and add two bars in either side of the shape | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Add mouse click listener to draw one or more lines from the output dot of '¦¦' shape | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Add mouse click listener to draw one or more lines to the input dot of '¦¦' shape | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Test the changes upon selection of the each shape and it's connectivity when dropped on each workspace | 0 | 0 | 1 | 0 | 0 | 0 | 1
|  | Total Hours | [6 empty] | 4