## Sheet1
Sprints | Sprint 1 | [7 empty] | Sprint 2
Tasks/Days | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
1. As a user, I want a frame with two panels and a menu to save and open a file, a button to add new tab and a button to compile.
a. Create a frame and add 2 panels. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Split panels Vertically. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Create a menu bar with 4 buttons Open, Save, New Space and Compile. | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. As a user, I should be able to to have a button "New Space" next to menu so that I can add a new tab the right panel.
a. Add a MouseListener on New Space button, so that whenever it is clicked a new tab should be added in the right panel.
b. Create the tabs named as Tab 1, Tab 2 and so on.
3. As a user, I want a rectangle shape at the top of the left panel with ')' symbol at its center and a dot right to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '(' at the center of rectangle.
c. Create a Component with dot. | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
d. Add the dot component near right side of rectangle. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
e. Add the rectangle button at the top of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. As a user, I want a rectangle below first rectangle with '(' symbol at its center and a dot left to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol ')' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
c. Add the dot component near left side of rectangle.
d. Add the rectangle button below first rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. As a user, I want a rectangle below second rectangle with '<' symbol at its center and 1 dot left and 2 dots right to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '<' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
c. Add 1 dot near left side and 2 dots near right side of rectangle.
d. Add the rectangle button below second rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. As a user, I want a rectangle below third rectangle with >' symbol at its center and 2 dots to left and 1 dot right to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '>' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
c. Add 1 dot near right side and 2 dots near left side of rectangle.
d. Add the rectangle button below third rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. As a user, I want a rectangle below fourth rectangle with '@' symbol at its center and 2 dots left and 2 dots right to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '@' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
c. Add 2 dots near right side and 2 dots near left side of rectangle.
d. Add the rectangle button below fourth rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. As a user, I want a rectangle below fifth rectangle with '¦¦' symbol at its center and 2 bars, one to left and other right to the symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '¦¦' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
c. Add 2 bars, one near left side and another near right side of rectangle.
d. Add the rectangle button below fifth rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. As a user, I want a rectangle below sixth rectangle with '-' symbol at its center and 2 dots, one to left and another right to symbol.
a. Create a Button with Rectangle shape. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add the text symbol '-' at the center of rectangle. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
c. Add 2 dots, one near left side and another near right side of rectangle.
d. Add the rectangle button below sixth rectangle of the left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. As a user, I should be able to select any of the shape in left panel by clicking on it.
a. Add action listener for all the shape objects of left panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Create a variable in singleton class to store all the data related to selected shape.
11. As a user, I should be able to click in the current tab so that the selected shape in left panel is drawn at the clicked position.
a. Add a Mouse click Listener on all the tabs in right panel. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
b. Add selected shape in right panel at the clicked position. | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12. As a user, I should be able to drag any shape in the right panel.
a. Add mouse pressed listener to all shape objects. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
b. Store the screen co-ordinates of the when mouse pressed event of the shape object occurs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
c. Repaint the object component at the co-ordinates. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
13. As a user, I should be able to save information in any shape.
a. Modify the mouse clicked listener to accommodate mouse double click event to open input dialouge box.
b. Store the string value entered in the in the input dialouge box.
14. As a user I should be able draw a line from dots.
a. Add mouse clicked listener to Dot component.
b. Store the co-ordinates of the Dot component when clicked.
c. Maintain a variable in singlton class to check if already clicked on Dot. | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0 | 1/2 | 0 | 0 | 0 | 0 | 0 | 0
d. Draw a line using paint component when clicked on another dot or Bar. | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
15. As a user I should be able to draw lines from bars.
a. Add mouse clicked listener to Bar component. | 0 | 0 | 4 | 3 | 3 | 3 | 2 | 2 | 0 | 4 | 3 | 3 | 3 | 2 | 2
b. Store the co-ordinates of the Bar component when clicked.
c. Maintain a variable in singleton class to check if Dot or a Bar is already clicked. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
d. Draw a line using paint component when clicked on another dot or Bar. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
16. As a system, I want any existing line to be dragged accordingly when any shape in right panel is dragged to a different position.
a. Store the new co-ordinates of the dragged shape and its dot and bar components. | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0
b. Repaint the line using new co-ordinates.
17. As a system, when user clicks on Compile button, I should be able to check if the graph drawn on current tab is correct.
a. Add Mouse Click Listener on Compile button to create graph from the shapes drawn in current tab.
b. Write a function to validate the graph.
c. Show a dialouge box represeting the output of compilation.
18. As a system, when user, clicks save, I should be able to save co-ordinates of all the shapes and lines in right panel into a file.
a. Add mouse click listener on Save button. | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
b. Add FileChooser event to select the directory and file name.
c. Add co-ordinates of shapes stored in right panel. | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
19. As a system, when user, opens a saved file, I should be able to redraw the shapes and lines in the right panel.
a. Add mouse click listener on open button. | 0 | 0 | 0 | 3 | 4 | 0 |  | 3 | 0 | 0 | 3 | 4 | 0 |  | 3
b. Add FileChooser event to select the directory and file name.
c. Read co-ordinates of different shapes from the file and store it. | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
d. Use the stored co-ordinates to repaint the shape objects. | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
20. Clean the code.