## Sheet1
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
As a user, I want to have "Add Workspace" button next to Menu option so that I can add new tab by clicking on it. | Create a Jbutton and name it "Add Workspace". Add the Jbutton to Menu bar next to Menu option. |  |  | 1
As a user, I want a new tab to be created alongside the existing tabs on click of "Add Workspace" button so that I can create multiple tabs. | Create a JTabbedPane which contains a workspace. Add a action listener to "Add Workspace" button to create new tab on every click. Each tab should have its own workspace where the user can draw shapes. |  |  |  | 4
As a user, I want to have (,),<,>,-<,¦¦,@ symbols in respective icons on the left panel, so that I can click on them and draw icons on the right panel. | Create seven Jbuttons corresponding to each of (,),<,>,-,@,¦¦ symbols. Add the jbuttons to left panel on load. |  |  |  | 4
As a user, I want to be able to click on right dot of one shape, then click on left dot of another shape in the workspace, so that I can draw a line between them. | Add condition check to allow users to draw lines from output(right) dot of one shape to input(left) dot of another shape. Create an arrow to the line pointing to input dot of the second shape. |  |  |  |  | 4
As a user, I want to have rectangular icon with "(" symbol in center, one dot to the right of the symbol, so that I can click the dots in the icon and draw lines. | Create a rectangular icon on right panel with "(" symbol on click of "(" icon on left panel. Create a dot inside the icon to the right of the symbol. |  |  |  |  | 1
As a user, I want to have rectangular icon with ")" symbol in center, one dot to the left of the symbol, so that I can click the dots in the icon and draw lines. | Create a rectangular icon on right panel with ")" symbol on click of ")" icon on left panel. Create a dot inside the icon to the left of the symbol. |  |  |  |  | 1
As a user, I want to have rectangular icon with "<" symbol in center, one dot to the left of the symbol, two dots to the right of the symbol, so that I can click the dots in the icon and draw lines. | Create a rectangular icon on right panel with "<" symbol on click of "<" icon on left panel. Create three dots inside the icon, one dot to the left of the symbol, two dots to the right of the symbol. |  |  |  |  | 1
As a user, I want to have rectangular icon with ">" symbol in center, one dot to the right of the symbol, two dots to the left of the symbol, so that I can click the dots in the icon and draw lines. | Create a rectangular icon on right panel with ">" symbol on click of ">" icon on left panel. Create three dots inside the icon, two dots to the left of the symbol, one dot to the right of the symbol. |  |  |  |  | 1
As a user, I want to have rectangular icon with "@" symbol in center and two dots to the right of the symbol and two dots to the left of the symbol, so that I can click the dots in the icon and draw lines. | Create a rectangular icon on right panel with "@" symbol on click of "@" icon on left panel. Create four dots inside the icon, two dots to the left of the symbol, two dots to the right of the symbol. |  |  |  |  | 1
As a user, I want to have rectangular icon with "-" symbol in center, one dot to the right of the symbol, one dot to the left of the symbol, so that I can click the dots in the icon and draw lines. | Create a rectangular icon on right panel with "-" symbol on click of "-" icon on left panel. Create two dots inside the icon, one dot to the left of the symbol, one dot to the right of the symbol. |  |  |  |  | 1
As a user, I want to have rectangular icon with "¦¦" symbol in center and one vertical bar to the right of the symbol, one vertical bar to the left of the symbol, so that I can click the dots in the icon and draw lines. | Create a rectangular icon on right panel with "¦¦" symbol on click of "¦¦" icon on left panel. Create two vertical bars inside the icon, one bar to the left of the symbol, one bar to the right of the symbol. |  |  |  |  | 1
As a user, I want to double click on any icon in the workspace so that I can add description to the icon. | Implement double click action listeners to open a dialog box. The string entered by the user is to be stored in the object class. | [11 empty] | 5
As a user, on clicking save button, I want to save all the tabs so that I can retrieve the tabs later. | On click of save button, all the open tabs along with all the associated workspaces are saved into a file. | [5 empty] | 3 | 3
As a user, on clicking load button, I want to load all the tabs so that I can view the tabs saved earlier. | On click of load button, all the saved tabs along with all the associated workspaces are loaded into the right panel. | [5 empty] | 3 | 3
As a developer, I want to learn about design patterns so that I can implement in my project. | Learn about Observer design pattern Gain knowledge about delegate design pattern. Acquired information about Factory design pattern. | 8
As a developer, I want to refactor the code to implement design patterns so that the complexity of code reduces. | Implement Observer design pattern on Workspace to handle mouse clicks and drags. |  | 3 | 3
As a developer, I want to refactor the code to implement design patterns so that the complexity of code reduces. | Implement Factory design pattern to create new shapes. |  | 3 | 3
As a developer, I want to refactor the code to implement design patterns so that the complexity of code reduces. | Implement singleton design pattern to share data among various classes. |  | 3 | 3
As a user, I want to have "Compile" button next to "Add Workspace" button so that I can compile my program. | Create a Jbutton and name it "Add Workspace". Add the Jbutton to Menu bar next to Menu option. |  |  | 1
As a user, I want to click on compile button and get an alert saying "Success" or "Failure" so that I can evaluate my connections. | Create adjacency list of all the icons starting from the "(" icon. Traverse each shape through the lines and validate against the following rules: 1. There should be one "(" icon and the lines should end at ")" icon 2. There should be ">" for every "<" icon. 3. One of the output dots in the "@"icon should have a line that connects to other icons and finally connects to one of the input dots of the same "@" icon. 4. "¦¦" icon should accept any number of connections and terminate that many connections. The result of Compilation should be displayed to user as a dialog box stating Compilation Success or Compilation Failure. | [7 empty] | 4 | 4 | 4 | 4 | 4
[14 empty] | Days Remaining | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1
[14 empty] | Tasks Remaining | 140 | 128 | 118 | 108 | 93 | 83 | 73 | 60 | 48 | 36 | 24 | 0
[14 empty] | Ideal | 140 | 127.3 | 114.6 | 101.9 | 89.2 | 76.5 | 63.8 | 51.1 | 38.4 | 25.7 | 13 | 0