## Sheet1
Student | User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
Ashwin | As a user, I need a shape - denoting “@” symbol, so that it acts as a looping structure. | Knowledge gathering on java graphics and custom shapes | 3 | 0 | 0 | 0 | 0 | 0 | 3
|  | Create a class structure for the looping shape and add corresponding attributes | 0 | 2 | 1 | 1 | 0 | 0 | 4
|  | Revamp the class structure to compily with the old panels and shapes and extend the code structure | 0 | 0 | 3 | 0 | 0 | 0 | 3
|  | Changes to add the input and output connectivity for the for loop | 0 | 0 | 1 | 2 | 1 | 0 | 4
|  | Changes to invalidate the connections from input to output | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Test the changes to check if the for loop and the connections are valid | 0 | 0 | 0 | 0 | 1 | 0 | 1
|  | Total Hours | [6 empty] | 16
Chandan | As a user, I should be able to save the current state of any number of tabs in a given workspace. | Knowledge Acquisition on Serializing Objects for multiple tabs | 2 | 0 | 0 | 0 | 0 | 0 | 2
|  | Store the saved states of only the saved tabs and write them to a file | 2 | 1 | 0 | 0 | 0 | 0 | 3
|  | Store the listOfShapes corresponding to each tab by fetching the current tab index | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Write the listOfShapes as separate files by serializing them | 0 | 1 | 1 | 1 | 0 | 0 | 3
|  | Discard the unsaved list of objects | 0 | 0 | 1 | 1 | 0 | 0 | 2
|  | Test the changes of the saved state of the object, different files corresponding to each list should be saved | 0 | 0 | 0 | 1 | 2 | 0 | 3
|  | Total Hours | [6 empty] | 15
Nachi | As a user, I need a “compile” button, so that I can validate the structure in the current tab. | Traverse through the given diagram and build a sparse matrix | 3 | 1 | 0 | 0 | 0 | 0 | 4
|  | Travese the sparse matrix and add the symbols to a stack. | 1 | 3 | 0 | 0 | 0 | 0 | 4
|  | Evauate the stack using push and pop operations to validate the approperiate symbols. | 0 | 2 | 2 | 1 | 0 | 0 | 5
|  | Using the sparse matrix check if input requirements for each shape are correct. | 0 | 0 | 1 | 1 | 1 | 0 | 3
|  | Using the sparse matrix check if output requirements for each shape are correct. | 0 | 0 | 0 | 1 | 1 | 0 | 2
|  | Unit test the changes to check if the compile function works as per requirements. | 0 | 0 | 0 | 0 | 2 | 0 | 2
|  | Total Hours | [6 empty] | 20
Chandan | As a user, I should be able to load the most recent state of any number of saved tabs in a given workspace. | Knowledge Acquisition on Serializing Objects for multiple tabs. | 2 | 0 | 0 | 0 | 0 | 0 | 2
|  | Read the saved states of only the saved tabs and load them from the files. | 2 | 1 | 0 | 0 | 0 | 0 | 3
|  | Load the listOfShapes corresponding to each tab by fetching the current indes of the saved tab index. | 0 | 2 | 0 | 0 | 0 | 0 | 2
|  | Read the listOfShapes as separate files by deserializing them | 0 | 1 | 1 | 1 | 0 | 0 | 3
|  | Load only the saved list of objects | 0 | 0 | 2 | 1 | 0 | 0 | 3
|  | Test the changes of the loaded state of the object, different files corresponding to each list should be loaded.All the tabs that were saved should be loaded back. | 0 | 0 | 0 | 1 | 1 | 0 | 2
|  | Total Hours | [6 empty] | 15
Srini | As a user I should be able to test each and every component in the frame, connect them and check the correctness of the validation. | Implementation of draw line functionality to connect two dots of a shape | 0 | 1 | 2 | 0 | 0 | 0 | 3
|  | Implementation of draw line functionality to draw many lines from a bar inside a rectangle | 0 | 0 | 0 | 1 | 0 | 0 | 1
|  | Code change to check only one line is drawn from a dot | 0 | 0 | 0 | 0 | 2 | 0 | 2
|  | Code change to check dots are not connected within a shape | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Hours | [6 empty] | 6
Ashutosh | As a user, I should be able to create a structure with all the desired shapes in one or multiple tabs and validate them. (Integration testing) | Add all the possile shapes on each of the tabs in the workspace. | 3 | 1 | 0 | 0 | 0 | 0 | 4
|  | Create multiple tabs. | 1 | 3 | 0 | 0 | 0 | 0 | 4
|  | Make all the connections among each shaape are per requirement. | 0 | 2 | 1 | 1 | 0 | 0 | 4
|  | Add values to the "-" shape. | 0 | 0 | 2 | 1 | 1 | 0 | 4
|  | Load and save the most recent state of all the diagrams on all the tabs. | 0 | 0 | 0 | 1 | 1 | 0 | 2
|  | The complie funtion is able to distinguish between correct and incorrect diagrams. | 0 | 0 | 0 | 0 | 2 | 0 | 2
|  | Total Hours | [6 empty] | 20